## Progress
INTERNSHIP - FPT ACADEMY Class: HCM23_CPL_React_03 Group: 01
Trello link: | trello.com
Timeline: | notion.site
Document link: | docs.google.com
Start date: | 2023-02-20
End date: | 2023-04-10
Member | Progress |  | Total task | Completed task
Thông |  | 76.47% | 17 | 13
Đạt |  | 85.71% | 14 | 12
Nhựt |  | 69.23% | 13 | 9
Khánh |  | 93.33% | 15 | 14
Duy |  | 84.62% | 13 | 11
Long |  | 6.667% | 15 | 1
SUM |  | 68.97% | 87 | 60

## Log
INTERNSHIP - FPT ACADEMY Class: HCM23_CPL_React_03 Group: 01
No. | Task name | Complexity | Detail | Assigned | Completed | Planned Week | Start | Planned Due | Completed | Note | Check PHASE2_ITG: - Service: Mock (50%), API (50%) | Check PHASE1_UI: - UI: completion (30%), similarity (20%), responsive (20%) - Reactive form/Data binding (30%)
| List of Training Programs - filter (Integrate) |  |  | Duy |  | 6 | 2023-03-22 | 2023-03-22 |  | 0% | Chưa thấy trên giao diện
1 | List of Training Programs - search (Integrate) | Medium |  | Duy | Duy | 7 | 2023-03-29 | 2023-03-29 | 2023-04-03 | 100%
2 | Training Program detail - detail (Integrate) | Medium |  | Duy | Duy | 7 | 2023-03-27 | 2023-03-27 | 2023-04-03 | 80% | Conflict SCSS
3 | Icons | Easy | navigation menu, navigator, document, action, indicator, delivery, other, status | Đạt | Đạt | 1 | 2023-02-16 | 2023-02-17 | 2023-02-16 | 100%
4 | Button | Easy | saving, navigation | Duy | Duy | 1 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 100%
5 | Progress Bar, Form search | Easy |  | Khánh | Khánh | 1 | 2023-02-16 | 2023-02-17 | 2023-02-17 | 100%
6 | Picker: time, date, month-year | Easy |  | Duy | Duy | 1 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 100%
7 | Filter | Easy |  | Thông | Thông | 1 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 100%
8 | Tooltip | Easy |  | Nhựt | Nhựt | 1 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 100%
9 | Table list | Easy | Training Calendar Table | Đạt | Đạt | 1 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 100%
| Import dialog |  |  | Long |  | 1 | 2023-02-16 | 2023-02-17 |  | 0%
11 | Login (UI) | Medium |  | Nhựt | Nhựt | 2 | 2023-02-20 | 2023-02-20 | 2023-02-22 | 100%
12 | List of Training Programs - view (UI) | Medium |  | Duy | Duy | 2 | 2023-02-20 | 2023-02-20 | 2023-03-07 | 100%
13 | Create Training Program - name (UI) | Medium |  | Long | Khánh | 2 | 2023-02-20 | 2023-02-20 | 2023-02-20 | 100% |  | Chưa responsive, chưa reactive form
14 | Create Training Program - general (UI) | Medium |  | Long | Long | 2 | 2023-02-20 | 2023-02-20 | 2023-03-16 | 100% |  | Form không dùng được, chưa responsive, chưa reactive form
15 | List of Syllabus (UI) | Medium |  | Khánh | Khánh | 2 | 2023-02-20 | 2023-02-21 | 2023-02-23 | 90% |  | UI chưa responsive, form search chưa có reactive -> JSON
16 | Training Calendar - general by day (UI) | Medium |  | Đạt | Đạt | 2 | 2023-02-20 | 2023-02-21 | 2023-03-08 | 90% |  | UI was changed base on requirement
17 | Create Class - add info (UI) | Medium |  | Thông | Thông | 2 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 100%
18 | Forgot password (UI) | Medium |  | Nhựt | Nhựt | 2 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 100%
19 | List of Training Programs - filter (UI) | Medium |  | Duy | Duy | 2 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 100%
20 | Create Syllabus - general (UI) | Medium |  | Nhựt | Nhựt | 2 | 2023-02-22 | 2023-02-22 | 2023-02-24 | 70% |  | Thiếu data binding
21 | Syllabus details - general (UI) | Medium |  | Khánh | Khánh | 2 | 2023-02-22 | 2023-02-22 | 2023-02-24 | 80% |  | thiếu responsive
22 | Training Program detail - general (UI) | Medium |  | Duy | Duy | 2 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 90% |  | Bug giao diện
23 | Create Class - tooltip1 (UI) | Medium |  | Thông | Thông | 2 | 2023-02-22 | 2023-02-22 | 2023-02-23 | 100%
24 | Syllabus details - outline (UI) | Medium |  | Khánh | Khánh | 2 | 2023-02-23 | 2023-02-23 | 2023-02-27 | 100%
25 | Training Calendar - week with search (UI) | Medium |  | Đạt | Đạt | 2 | 2023-02-23 | 2023-02-23 | 2023-03-08 | 90% |  | UI was changed based on requirement
26 | Create Class - tooltip2 (UI) | Complex |  | Thông | Thông | 2 | 2023-02-23 | 2023-02-23 | 2023-02-28 | 100% |  | Cần fix
| Create Training Program - name (Integrate) |  |  | Long |  | 3 |  |  |  | 50% | Trả sai định dạng JSON
| Create Training Program - general (Integrate) |  |  | Long |  | 3 |  |  |  | 0% | Chưa hoàn thiện
| Create Training Program - syllabus (Integrate) |  |  | Long |  | 3 |  |  |  | 0% | Chưa hoàn thiện
| Create Training Program - import (Integrate) |  |  | Long |  | 3 |  |  |  | 0% | Chưa hoàn thiện
| Import Syllabus (Integrate) |  |  | Long |  | 3 |  |  |  | 0% | Chưa hoàn thiện
32 | User management - search (UI) | Medium |  | Nhựt | Nhựt | 3 | 2023-03-02 | 2023-03-02 | 2023-03-10 | 100% |  | Chưa data binding
33 | Syllabus details - other (UI) | Medium |  | Khánh | Khánh | 3 | 2023-02-27 | 2023-02-27 | 2023-02-28 | 100% |  | Chưa responsive
34 | Create Class - add syllabus (UI) | Medium |  | Khánh | Khánh | 3 | 2023-03-06 | 2023-03-07 | 2023-03-05 | 100%
35 | Training Program detail - detail (UI) | Medium |  | Duy | Duy | 3 | 2023-02-27 | 2023-03-03 | 2023-03-07 | 70% |  | thiếu data binding
36 | Training Program detail - material (UI) | Medium |  | Duy | Duy | 3 | 2023-02-28 | 2023-03-03 | 2023-03-08 | 100%
| User management - general (Integrate) |  |  | Long |  | 3 |  |  |  | 0%
| Training Program detail - material (Integrate) |  |  | Duy |  | 7 | 2023-03-28 | 2023-03-28
39 | Training Calendar - filter (UI) | Medium |  | Đạt | Đạt | 3 | 2023-02-27 | 2023-02-27 | 2023-03-06 | 100%
40 | List of Class - general (UI) | Medium |  | Đạt | Đạt | 3 | 2023-02-28 | 2023-02-28 | 2023-03-10 | 90%
41 | List of Class - filter (UI) | Medium |  | Đạt | Đạt | 3 | 2023-03-01 | 2023-03-01 | 2023-03-07 | 90%
42 | Create Class - add name(UI) | Easy |  | Thông | Thông | 3 | 2023-02-27 | 2023-02-27 | 2023-02-28 | 100%
43 | Create Class - add program (UI) | Medium |  | Thông | Thông | 3 | 2023-02-28 | 2023-02-28 | 2023-03-06 | 100%
44 | Login (Integrate) | Medium |  | Nhựt | Nhựt | 3 | 2023-03-01 | 2023-03-01 | 2023-03-06 | 100%
45 | List of Training Programs - view (Integrate) | Medium |  | Duy | Duy | 3 | 2023-03-03 | 2023-03-10 | 2023-03-10 | 100%
46 | List of Syllabus (Integrate) | Medium |  | Khánh | Khánh | 3 | 2023-03-01 | 2023-03-02 | 2023-03-13 | 80% | Lỗi API
| User management - import (Integrate) |  |  | Đạt |  | 6 | 2023-03-21 | 2023-03-21
48 | Nav-bar buttons | Medium |  | Thông | Thông | 3 | 2023-03-03 | 2023-03-03 | 2023-03-08 | 100%
49 | Create Class - create syllabus (UI) | Medium |  | Khánh | Khánh | 4 | 2023-03-02 | 2023-03-02 | 2023-03-05 | 90%
50 | Authentication | Complex | Interceptor, request header, logout | Thông | Thông | 4 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 100%
51 | Home page (UI) | Medium |  | Thông | Thông | 5 | 2023-03-15 | 2023-03-15 | 2023-03-16 | 100%
52 | Class details - general (UI) | Medium |  | Thông | Thông | 5 | 2023-03-16 | 2023-03-17 | 2023-03-17 | 100%
| Create Training Program - syllabus (UI) |  |  | Long |  | 6 | 2023-03-20 | 2023-03-21 |  | 80% |  | Thiếu responsive
| Create Training Program - import (UI) |  |  | Long |  | 6 | 2023-03-22 | 2023-03-22 |  | 25% | Thiếu service | 50%
| Import Syllabus (UI) |  |  | Long |  | 6 | 2023-03-23 | 2023-03-23 |  | 25% | Thiếu service | 50%
56 | Training Calendar - filter (Integrate) | Medium |  | Đạt | Đạt | 6 | 2023-03-20 | 2023-03-20 | 2023-03-27 | No API (back-end)
57 | List of Class - general (Integrate) | Medium |  | Đạt | Đạt | 6 | 2023-03-21 | 2023-03-21 | 2023-04-03 | 80% | incomplete delete
58 | List of Class - search (Integrate) | Medium |  | Đạt | Đạt | 7 | 2023-03-29 | 2023-03-29 | 2023-04-03 | API bugs
59 | Forgot password (Integrate) | Medium |  | Nhựt | Nhựt | 6 | 2023-03-21 | 2023-03-21 | 2023-03-27 | 100% | Chưa hoàn thiện
60 | List of Syllabus - search (Integrate) | Medium |  | Khánh | Khánh | 7 | 2023-03-29 | 2023-03-29 | 2023-04-03
61 | Syllabus details - general (Integrate) | Medium |  | Khánh | Khánh | 6 | 2023-03-20 | 2023-03-20 | 2023-04-03 | 100% | Chưa hoàn thiện
62 | Syllabus details - outline (Integrate) | Medium |  | Khánh | Khánh | 6 | 2023-03-21 | 2023-03-22 | 2023-04-03 | 100% | in error
63 | Syllabus details - other (Integrate) | Medium |  | Khánh | Khánh | 6 | 2023-03-23 | 2023-03-24 | 2023-04-03 | 100% | in error
64 | Training Program detail - general (Integrate) | Medium |  | Duy | Duy | 6 | 2023-03-23 | 2023-03-23 | 2023-03-27 | 90% | Sai UI
| Create Class - add trainer (UI) |  |  | Khánh |  | 6 | 2023-03-20 | 2023-03-20 |  | 0%
66 | Create Class - add syllabus (Integrate) | Medium |  | Khánh | Khánh | 7 | 2023-03-27 | 2023-03-28 | 2023-04-03 | 90% | sai vị trí logic
| User management - permission (Integrate) |  |  | Nhựt |  | 3 |  |  |  | 0%
68 | Create Syllabus - outline (UI) | Medium |  | Nhựt | Nhựt | 6 | 2023-03-20 | 2023-03-20 | 2023-04-03 | 80% |  | chưa giống Figma
69 | Create Syllabus - other (UI) | Medium |  | Nhựt | Nhựt | 6 | 2023-03-23 | 2023-03-23 | 2023-04-03 | 80% |  | chưa giống Figma
| Create Syllabus - general (Integrate) |  |  | Nhựt |  | 6 | 2023-03-22 | 2023-03-22 |  | 25% | in error
| User management - permission (UI) |  |  | Nhựt |  | 7 | 2023-03-28 | 2023-03-29 |  | 0% |  | Form không dùng được, chưa responsive, chưa reactive form
| Create Syllabus - other (Integrate) |  |  | Nhựt |  | 7 | 2023-03-28 | 2023-03-28
| Create Class - add info (Integrate) |  |  | Thông |  | 6 | 2023-03-22 | 2023-03-22 |  | 0% | Chưa hoàn thiện
| Create Class - add name(Integrate) |  |  | Thông |  | 6 | 2023-03-22 | 2023-03-22 |  | 0%
75 | List of Class - filter (Integrate) | Medium |  | Đạt | Đạt | 6 | 2023-03-22 | 2023-03-22 | 2023-03-27 | 100%
| Create Class - add program (Integrate) |  |  | Thông |  | 6 | 2023-03-22 | 2023-03-22 |  | 0%
| User management - import (UI) |  |  | Long |  | 6 | 2023-03-20 | 2023-03-20 |  | 0% |  | Chưa thấy trên giao diện
78 | Training Calendar - general by week (UI) | Medium |  | Đạt | Đạt | 7 | 2023-03-27 | 2023-03-27 | 2023-03-27 | 100%
| User management - general (UI) |  |  | Long |  | 7 | 2023-03-27 | 2023-03-27 |  | 30% |  | Chưa responsive, chưa reactive form
80 | Create Class - view syllabus (UI) | Medium |  | Thông | Thông | 6 | 2023-03-21 | 2023-03-21 | 2023-04-03 | 100%
81 | Create Class - view syllabus (Integrate) | Medium |  | Thông | Thông | 7 | 2023-03-27 | 2023-03-28 | 2023-04-03 | 100%
82 | Class details - general (Integrate) | Medium |  | Thông | Thông | 7 | 2023-03-30 | 2023-03-30 | 2023-04-03 | 100
| Create Class - add trainer (Integrate) |  |  | Khánh |  | 7 | 2023-03-29 | 2023-03-29 |  | 0%
| User management - search (Integrate) |  |  | Long |  | 7 | 2023-03-30 | 2023-03-30
| Training Calendar - general by day (Integrate) |  |  |  |  | 0 |  |  |  | 0% | Chưa hoàn thiện
| Training Calendar - general by week (Integrate) |  |  |  |  | 0 |  |  |  | 0%
| Training Calendar - week with search (Integrate) |  |  |  |  | 0 | 2023-03-28 | 2023-03-28 |  | 0%
| Create Syllabus - outline (Integrate) | [8 empty] | 0%
| Comming Soon (UI) |  |  | Đạt |  |  | 2023-03-28 | 2023-03-28
| Deploy |  |  | Thông |  |  | 2023-03-31 | 2023-04-04

## Components
No. | Component | Common | Screen | Function
1 | login | X | Login | Authentication
2 | forgot password |  | Forgot password | Authentication
3 | search | X | List of Syllabus | List of Syllabus
4 | created date
5 | add syllabus
6 | popup menu
7 | import syllabus
8 | duplicate control
9 | import setting |  | Import Syllabus | List of Syllabus
10 | scheme
11 | delivery priciple
12 | active
13 | unit
14 | time allocation |  | Syllabus details - general | Syllabus Details
15 | syllabus name |  | Syllabus details - outline | Syllabus Details
16 | manage
17 | code
18 | version
19 | level
20 | Attendee number
21 | technical requirement(s)
22 | course objectives
23 | save
24 | scheme |  | Syllabus details - other | Syllabus Details
25 | delivery priciple
26 | active
27 | unit
28 | time allocation
29 | delivery type |  | Create Syllabus - general | Create Syllabus
30 | soft unit
31 | time allocation
32 | alert popup
33 | delete day
34 | upload file
35 | add day |  | Create Syllabus - outline | Create Syllabus
36 | delivery principle
37 | search syllabus |  | Create Syllabus - other | Create Syllabus
38 | search program |  | List of Training Programs - view programs | List of Training Program
39 | filter program | X
40 | import program | X
41 | add program
42 | filter program |  | List of Training Programs - filter | List of Training Program
43 | delivery type |  | Training Program detail - general | Training Program Details
44 | time allocation
45 | delete day
46 | time allocation |  | Training Program detail - detail | Create Training Program
47 | content program
48 | day program |  | Training Program detail - material | Create Training Program
49 | edit program
50 | delete program
51 | import setting |  | Create Training Program - import | Create Training Program
52 | duplicate control
53 | Program name |  | Create Training Program - name | Create Training Program
54 | Select syllabus |  | Create Training Program - syllabus | Create Training Program
55 | search
56 | save
57 | time allocation |  | Create Training Program - general | Create Training Program
58 | cotent
59 | delete program
60 | Select syllabus
61 | search
62 | save
63 | search class |  | List of Class - general | List of Class
64 | filter class
65 | location tab |  | List of Class - filter | List of Class
66 | time frame
67 | class time
68 | status
69 | attendee
70 | FSU
71 | Trainer
72 | edit class |  | List of Class - popup menu | List of Class
73 | duplicate class
74 | delete class
75 | title info |  | Class details - general | Class Details
76 | general info
77 | time frame
78 | attendee
79 | training program
80 | trainer popup
81 | notification popup
82 | name form |  | Create Class - add name | Create Class
83 | search program |  | Create Class - add program | List of Syllabus
84 | blank tabs
85 | popup |  | Create Class - tooltip1 | Create Class
86 | popup |  | Create Class - tooltip2 | Create Class
87 | add name |  | Create Class - add info | Create Class
88 | title info
89 | general info
90 | time frame
91 | attendee
92 | program detail
93 | title info |  | Create Class - add trainer | Create Class
94 | syllabus detail
95 | title info |  | Create Class - view syllabus | Create Class
96 | general info
97 | time frame
98 | attendee
99 | training program tab
100 | current content |  | Create Class - add syllabus | Create Class
101 | add syllbus
102 | title info
103 | select syllabus
104 | create syllabus dialog |  | Create Class - create syllabus | Create Class
105 | search tab |  | Training Calendar - general by day | Training Calendar
106 | calendar
107 | timetable for class
108 | search tab |  | Training Calendar - general by week | Training Calendar
109 | calendar
110 | timetable for class
111 | location tab |  | Training Calendar - filter | Training Calendar
112 | time frame
113 | class time
114 | status
115 | attendee
116 | FSU
117 | Trainer
118 | search tab |  | Training Calendar - week with filter | Training Calendar
119 | month dropdown
120 | year dropdown
121 | timetable for class
122 | filter user |  | User management - general | User Management
123 | add new |  | User management - search | User Management
124 | add new |  | User management - permission | User Management
125 | Role name
126 | Syllabus dropdown
127 | Training program drop down
128 | Class dropdown
129 | Learning material dropdown
130 | import setting |  | User management - import | User Management
131 | Duplicate control

## References
Functions' name | Student ID | Team role | Email | First Name | Full name | Complexity
List of Syllabus | CE150011 | Member | DuyTHCE150011@fpt.edu.vn | Duy | Trần Hoàng Duy | Easy
Syllabus Details | CE150703 | Member | KhanhHCE150703@fpt.edu.vn | Khánh | Huỳnh Khánh | Medium
Create Syllabus | CE160255 | Member | NhutNMCE160255@fpt.edu.vn | Nhựt | Nguyễn Minh Nhựt | Complex
List of Training Program | SE150508 | Member | LongLCNSE150508@fpt.edu.vn | Long | Lê Cáp Ngọc Long
Training Program Details | SE160850 | Leader | thongntse160850@fpt.edu.vn | Thông | Nguyễn Trung Thông
Create Training Program | SE162102 | Member | dattkse162102@fpt.edu.vn | Đạt | Trần Kim Đạt
List of Class
Class Details
Create Class
Training Calendar
User Management
Authentication
Deploy

## Screen
No. | Screen | Assigned | Note | Illustration Icon | Member | Number of screens
1 | Login | Nhựt |  | 📯 | Nhựt | 6
2 | Forgot password | Nhựt |  | 🚀 | Khánh | 6
3 | List of Syllabus | Khánh |  | 🎀 | Duy | 6
4 | Import Syllabus | Long |  | ⚒️ | Long | 7
5 | Syllabus details - general | Khánh |  | 📅 | Đạt | 7
6 | Syllabus details - outline | Khánh |  | 🌲 | Thông | 7
7 | Syllabus details - other | Khánh |  |  | SUM | 39
8 | Create Syllabus - general | Nhựt
9 | Create Syllabus - outline | Nhựt
10 | Create Syllabus - other | Nhựt
11 | List of Training Programs - view programs | Duy
12 | List of Training Programs - filter | Duy
13 | Training Program detail - general | Duy
14 | Training Program detail - detail | Duy
15 | Training Program detail - material | Duy
16 | Create Training Program - import | Long
17 | Create Training Program - name | Long
18 | Create Training Program - syllabus | Long
19 | Create Training Program - general | Long
20 | List of Class - general | Đạt
21 | List of Class - filter | Đạt
22 | Class details - general | Đạt
23 | Create Class - add name | Thông
24 | Create Class - add program | Thông
25 | Create Class - tooltip1 | Thông
26 | Create Class - tooltip2 | Thông
27 | Create Class - add info | Thông
28 | Create Class - add trainer | Thông
29 | Create Class - view syllabus | Thông
30 | Create Class - add syllabus | Khánh
31 | Create Class - create syllabus | Khánh
32 | Training Calendar - general by day | Đạt
33 | Training Calendar - general by week | Đạt
34 | Training Calendar - filter | Đạt
35 | Training Calendar - week with search | Đạt
36 | User management - general | Long
37 | User management - search | Nhựt
38 | User management - permission | Long
39 | User management - import | Duy