## ProjectSchedule (devided)
FA
|  | Project Start: | 2023-02-10
|  | Today: | 2023-02-15
|  | Display Week: | 1 |  |  | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27
 | time axis 2023-02-06 to 2023-04-02
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-02-06 to 2023-04-02
Create login page ( UI + Validate ) | KhanhH, NhutNM |  | 2023-02-10 | 2023-02-12 | 3
Create login page ( Integrate ) | KhanhH, NhutNM |  | 2023-02-13 | 2023-02-15
Create page List Syllabus ( UI ) | KhanhH, NhutNM |  | 2023-02-10 | 2023-02-13 | 4
Create page List Syllabus ( Integrate api ) | KhanhH, NhutNM |  | 2023-02-14 | 2023-02-16 | 3
Create page import excel ( UI ) | KhanhH, NhutNM |  | 2023-02-17 | 2023-02-19 | 3
Create Syllabus (Add, Edit, View) | KhanhH, NhutNM |  | 2023-02-10 | 2023-03-10 | 29
Create page list trainning program ( UI ) | LongLCN, DuyTH |  | 2023-02-10 | 2023-02-13
Create page list trainning program ( Integrate api ) | LongLCN, DuyTH |  | 2023-02-14 | 2023-02-16
Create import excel | LongLCN, DuyTH |  | 2023-02-17 | 2023-02-19
Create trainning (Add, Edit, View) | LongLCN, DuyTH |  | 2023-02-10 | 2023-03-10
Create page list class ( UI ) | DatTK, ThongNT |  | 2023-02-10 | 2023-02-13 | 4
Create page list class ( Integrate ) | DatTK, ThongNT |  | 2023-02-14 | 2023-02-16
Create import excel | DatTK, ThongNT |  | 2023-02-17 | 2023-02-19 | 3
Create class (Add, Edit, View) | DatTK, ThongNT |  | 2023-02-10 | 2023-03-10
Create page list user ( UI ) | LongLCN, DuyTH |  | 2023-02-10 | 2023-02-13
Create page list user ( Integrate ) | LongLCN, DuyTH |  | 2023-02-14 | 2023-02-16
Create import excel | LongLCN, DuyTH |  | 2023-02-17 | 2023-02-19
Create user | DatTK, ThongNT |  | 2023-02-20 | 2023-03-10
Create trainning Calendar | DatTK, ThongNT |  | 2023-02-10 | 2023-03-10
Insert new rows ABOVE this one
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## ProjectSchedule W1
FA
|  | Project Start: | 2023-02-10
|  | Today: | 2023-02-15
|  | Display Week: | 1 |  |  | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27
 | time axis 2023-02-06 to 2023-04-02
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-02-06 to 2023-04-02
Create login page ( Review SRS + write JSON format document ) | KhanhH, NhutNM |  | 2023-02-09 | 2023-02-10
Create login page ( UI + Validate Code) | KhanhH, NhutNM |  | 2023-02-10 | 2023-02-12 | 3
Create login page ( Integrate ) |  |  | 2023-02-13 | 2023-02-15
Create page List Syllabus ( UI Review SRS + write JSON format document ) | KhanhH, NhutNM |  | 2023-02-09 | 2023-02-10 | 2
Create page List Syllabus ( UI ) | KhanhH, NhutNM |  | 2023-02-10 | 2023-02-13 | 4
Create page List Syllabus ( Integrate api ) |  |  | 2023-02-14 | 2023-02-16 | 3
Create page import excel ( UI ) |  |  | 2023-02-11 | 2023-02-19 | 9
Create Syllabus (Add, Edit, View - Review SRS + write JSON format document ) | KhanhH, NhutNM |  | 2023-02-09 | 2023-02-10 | 2
Create Syllabus (Add, Edit, View) | KhanhH, NhutNM |  | 2023-02-12 | 2023-03-10 | 27
Create page list trainning program ( UI Review SRS + write JSON format document ) | LongLCN, DuyTH |  | 2023-02-09 | 2023-02-10
Create page list trainning program ( Integrate api ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19
Create trainning (Add, Edit, View - Review SRS + write JSON format document ) | LongLCN, DuyTH |  | 2023-02-09 | 2023-02-10
Create trainning (Add, Edit, View ) | LongLCN, DuyTH |  | 2023-02-10 | 2023-03-10
Create page list class ( UI - Review SRS + write JSON format document ) | DatTK, ThongNT |  | 2023-02-09 | 2023-02-10 | 2
Create page list class ( UI ) | DatTK, ThongNT |  | 2023-02-10 | 2023-02-13 | 4
Create page list class ( Integrate ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19 | 3
Create class (Add, Edit, View - Review SRS + write JSON format document ) | DatTK, ThongNT |  | 2023-02-09 | 2023-02-10
Create class (Add, Edit, View ) | DatTK, ThongNT |  | 2023-02-10 | 2023-03-10
Create page list user ( UI Review SRS + write JSON format document ) | LongLCN, DuyTH |  | 2023-02-09 | 2023-02-10
Create page list user ( UI ) | LongLCN, DuyTH |  | 2023-02-10 | 2023-02-13
Create page list user ( Integrate ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19
Create user |  |  | 2023-02-20 | 2023-03-10
Create trainning Calendar ( Review SRS + write JSON format document ) | DatTK, ThongNT |  | 2023-02-09 | 2023-02-10
Create trainning Calendar | DatTK, ThongNT |  | 2023-02-10 | 2023-03-10
Insert new rows ABOVE this one
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## ProjectSchedule W2
FA
|  | Project Start: | 2023-02-10
|  | Today: | 2023-02-15
|  | Display Week: | 1 |  |  | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27
 | time axis 2023-02-06 to 2023-04-02
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-02-06 to 2023-04-02
Create login page ( Review SRS + write JSON format document ) | KhanhH, NhutNM |  | 2023-02-09 | 2023-02-10
Create login page ( UI + Validate Code) | KhanhH, NhutNM |  | 2023-02-10 | 2023-02-12 | 3
Create login page ( Integrate ) |  |  | 2023-02-13 | 2023-02-15
Create page List Syllabus ( UI Review SRS + write JSON format document ) | KhanhH, NhutNM |  | 2023-02-09 | 2023-02-10 | 2
Create page List Syllabus ( UI ) | KhanhH, NhutNM |  | 2023-02-10 | 2023-02-13 | 4
Create page List Syllabus ( Integrate api ) |  |  | 2023-02-14 | 2023-02-16 | 3
Create page import excel ( UI ) |  |  | 2023-02-11 | 2023-02-19 | 9
Create Syllabus (Add, Edit, View - Review SRS + write JSON format document ) | KhanhH, NhutNM |  | 2023-02-09 | 2023-02-10 | 2
Create Syllabus (Add, Edit, View) | KhanhH, NhutNM |  | 2023-02-12 | 2023-03-10 | 27
Create page list trainning program ( UI Review SRS + write JSON format document ) | LongLCN, DuyTH |  | 2023-02-09 | 2023-02-10
Create page list trainning program ( Integrate api ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19
Create trainning (Add, Edit, View - Review SRS + write JSON format document ) | LongLCN, DuyTH |  | 2023-02-09 | 2023-02-10
Create trainning (Add, Edit, View ) | LongLCN, DuyTH |  | 2023-02-10 | 2023-03-10
Create page list class ( UI - Review SRS + write JSON format document ) | DatTK, ThongNT |  | 2023-02-09 | 2023-02-10 | 2
Create page list class ( UI ) | DatTK, ThongNT |  | 2023-02-10 | 2023-02-13 | 4
Create page list class ( Integrate ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19 | 3
Create class (Add, Edit, View - Review SRS + write JSON format document ) | DatTK, ThongNT |  | 2023-02-09 | 2023-02-10
Create class (Add, Edit, View ) | DatTK, ThongNT |  | 2023-02-10 | 2023-03-10
Create page list user ( UI Review SRS + write JSON format document ) | LongLCN, DuyTH |  | 2023-02-09 | 2023-02-10
Create page list user ( UI ) | LongLCN, DuyTH |  | 2023-02-10 | 2023-02-13
Create page list user ( Integrate ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19
Create user |  |  | 2023-02-20 | 2023-03-10
Create trainning Calendar ( Review SRS + write JSON format document ) | DatTK, ThongNT |  | 2023-02-09 | 2023-02-10
Create trainning Calendar | DatTK, ThongNT |  | 2023-02-10 | 2023-03-10
Insert new rows ABOVE this one
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.
Note on B7: Thong Nguyen Trung: - nếu SRS chưa rõ phải → tổng hợp đưa lên BA - Json format để gửi cho BE (sáng mai)

## ProjectSchedule
FA
|  | Project Start: | 2023-02-10
|  | Today: | 2023-02-15
|  | Display Week: | 1 |  |  | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27
 | time axis 2023-02-06 to 2023-04-02
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-02-06 to 2023-04-02
Create login page ( UI + Validate ) | 1 |  | 2023-02-10 | 2023-02-12 | 3
Create login page ( Integrate ) |  |  | 2023-02-13 | 2023-02-15
Create page List Syllabus ( UI ) | 1 |  | 2023-02-10 | 2023-02-13 | 4
Create page List Syllabus ( Integrate api ) |  |  | 2023-02-14 | 2023-02-16 | 3
Create page import excel ( UI ) |  |  | 2023-02-17 | 2023-02-19 | 3
Create Syllabus (Add, Edit, View) |  |  | 2023-02-10 | 2023-03-10 | 29
Create page list trainning program ( UI ) |  |  | 2023-02-10 | 2023-02-13
Create page list trainning program ( Integrate api ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19
Create trainning (Add, Edit, View) |  |  | 2023-02-10 | 2023-03-10
Create page list class ( UI ) |  |  | 2023-02-10 | 2023-02-13 | 4
Create page list class ( Integrate ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19 | 3
Create class (Add, Edit, View) |  |  | 2023-02-10 | 2023-03-10
Create trainning Calendar |  |  | 2023-02-10 | 2023-03-10
Create page list user ( UI ) |  |  | 2023-02-10 | 2023-02-13
Create page list user ( Integrate ) |  |  | 2023-02-14 | 2023-02-16
Create import excel |  |  | 2023-02-17 | 2023-02-19
Create user |  |  | 2023-02-20 | 2023-03-10
Insert new rows ABOVE this one
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Members
Member
LongLCN
DatTK
ThongNT
KhanhH
DuyTH
LongLCN, DuyTH
DatTK, ThongNT
KhanhH, NhutNM